## Slide 1: Harvey Nash Scrum Process NHI HUYNH-PQA, CSM

## Slide 2: Outline
Scrum Framework
Harvey Nash Scrum Process and template
Q&A, Examination

## Slide 3: You will learn
The Why of Scrum
The What of Scrum
The How of Scrum:
  Scrum Roles
  Sprinting
  Reports
Apply Harvey Nash Scrum process

## Slide 4: Scrum Principal

## Slide 5: Why is Scrum?
Penny Game
  2 teams, each team has 5 members, 5 supervisers, 1 PO, 1 User
  Circle life: 10 paths, 5 paths, 2 paths, 1 path
  Rule: measure effort each circle
What things do you realize?
  Smaller batches produce faster cycle times
  Water Fall has Plan driven approach
  Scrum has Value driven approach

## Slide 6: What is Scrum?
Scrum is:
A framework for product
Development in Complex and
Chaotic
An Empirical process
Notes: Chaotic: kei’otik: lộn xộn
Empirical: kinh nghiem chu nghia

## Slide 7: The Foundations of Scrum
Cross functional team
Single works stream
Time boxing
(Re)Defining Done
Progressive elaboration
Self Organization
Notes: Cross functional team: major resource
Single works stream: sprint, user story (Stream: luồng, dòng)
Time boxing: how many stuff you can do in sprint  Velocity
(Re)Defining Done: Done or Not done. There is no 80% complete
Progressive elaboration: xây dung su tien bo: Retrospective, increase velocity
Self Organization: why?  avoid bottle neck, depend on somebody  Gioi han cua Self Organization?  in sprint

## Slide 8: Three pillars of Scrum
Transparency: the progress of the work and the team is visible to all.
  Inspection: frequent opportunities to review the current state of the work and how the team is using Scrum.
  Adaptation: to follow inspection, it is critical to make changes and adapt to the new ideas, information, and current environment of the work

## Slide 9: Scrum Overview

## Slide 10: Project Road Map

## Slide 11: To Start Up
Sprint 0: To “setup” a project or product, to do non-functional work
Notes: Key things:
Objectives
Tools
Architecture
Training….

## Slide 12: Sprint Overview

## Slide 13: 3 most important things in Scrum
3 Roles:
  Product Owner
  Scrum Master
  Scrum Team
4 Events:
  Planning meeting
  Daily meeting
  Sprint review meeting
  Retrospective meeting
3 Artifacts:
  Product backlog (store User Story with priority)
  Sprint log
  Reports (Burndown Charts)

## Slide 14
Scrum Roles
Product Owner
Scrum Master
Scrum Team
Stakeholders & Users
Security Clasification: Internal
Notes: PO: What to build
Team: How to build
Scrum master: facility: make sure team build fast and stable

## Slide 15: How do Scum work?
Based on 4 events:
Planning meeting: Sprint goal + tasks
1st stage:
  Present the highest priority Product Backlog.
  Review and clarify each item user story points
  Break each story into tasks and clearly defined acceptance criteria (Define sprint goal)
2nd stage:
  Estimate for each task : each task should be <=16hrs
  Commitment to complete the tasks.
  Update to sprint backlog

## Slide 16: How do Scrum work?
2. Daily meeting:

## Slide 17: How do Scrum work?
3. Sprint review meeting: Show
“Done” Story
Incomplete Story
Scrum Team
Accept/Reject
Put in Product Backlog
Product Owner
Demo
Inform
Security Classification: Internal
Notes: What will be happened if Scrum Team can’t complete Story?  Don’t move to next Sprint

## Slide 18: How do Scrum work?
4. Retrospective meeting: 3 questions
What went well during the last sprint?
What could be improved in the next sprint?
Action need

## Slide 19: Artifact: The Product Backlog
Backlog Item | Estimate | Priority
As a Conference Room Coordinator I want to allow a Guest to make a reservation in the system so that we can book their request for a conference room in our system. | Large (4 –6) | 1
 Things you get

## Slide 20: Artifact: Sprint log, Task Board
https://jira.harveynash.vn/secure/Dashboard.jspa
 Things you do

## Slide 21: Report: Release Burndown Chart
0 hrs.
Notes: Release burndown :
Show: sum total of estimated work remaining in Product Backlog for the current Release and current burn rate
Used to : manage Release
Owner: product owner

## Slide 22: Report: Sprint Burndown Chart
Notes: Sprint burndown:
Show: sum total of estimated tasks remaining in the Sprint Log and current burn
Used to: manage sprint
Owner: Team

## Slide 23: Report: Velocity Chart
Notes: Velocity chart:
Show: Historical rate of project delivery
Used to: assess impact of impediment removal
Owner: Scrum Master

## Slide 24: Harvey Nash Scrum Process

## Slide 25: How HvN Scrum is difference?
3 Roles:
  Product Owner
  Scrum Master
  Scrum Team  BA, TA, Dev, QC
4 Events: including management processes
  Planning meeting
  Daily meeting
  Sprint review meeting
  Retrospective meeting
3 Artifacts: Output from standard processes
  Product backlog (store User Story with priority)
  Sprint log
  Reports (Burndown Charts)

## Slide 26: HvN Scrum Process Characteristics
Belong to Harvey Nash Software Development Process Standard
Combine Scrum framework and CMMI best practice to:
  Suitable for Harvey Nash
  Add the best value to org and customer

## Slide 27: Criteria for Harvey Nash Scrum Approach
Project type is not fixed price. It should be ODC, T&M
Client and Project team members have good awareness on SCRUM.
Product Owner, Scrum master, Scrum Team are clearly defined.
Product Owner is Client (or representative ) and make sure they have time to stay with development team for queries and explanation on stories. (It should be at least 2 hours/day)
Development team are self-organising

## Slide 28: HvN Scrum Roles
Product Owner
The Team
Scrum Master
Business Analyst
Project Manager
Stakeholders & Users
Developer
Tester
Architect
Project Director

## Slide 29: HvN Scrum Rule
Sprint duration is never extended
The Product Owner is one person
SAD must be done at sprint 0
Processes (such as Project Monitoring and Control, Coding, Testing process...) in Scrum project are referred to standard processes
Design note must be provided for user stories

## Slide 30: HvN Scrum: How to work
Items | Definition of Done
Sprint 0 | Project team is trained about Scrum Process.
 | All committed work products in approved tailoring sheet have to be completed according to SLA.
 | SAD is ready
 | Coding Convention and Code review checklist must be approved in case client doesn’t require using their standard Development, testing environment and testing device are ready.
 | All agreement, commitments have to be transferred to project team members.
 | All dependencies impact on Sprint 1 back log are resolved.
 | Requirement for Sprint 1 is approved by PO.
 | Build script, build guide is developed

## Slide 31: HvN Scrum: How to work
Items | Definition of Done
A US/PBI | US is provided or approved by Product Owner.
 | US is transferred and understood by the team.
 | Tasks for US are identified and estimated by the team.
 | Design note is provided for US if required
 | Code is completed and passed code review with zero open defect.
 | Unit tests are completed and passed.
 | Acceptance criteria of user story are passed.
 | Test cases are generated as approach which mentioned in test strategy.
 | All cases of the test case have been are executed and passed
A Successful Sprint | All committed US/PBI are done.
 | There are no Critical and Major bugs.
 | Unit test has to cover at least 70% of the source code.

## Slide 32: HvN Scrum tool
Product Backlog: https://jira.harveynash.vn

## Slide 33: HvN Scrum Tool
Sprint Log: https://jira.harveynash.vn

## Slide 34: HvN Scrum Tool
Task Board: https://jira.harveynash.vn

## Slide 35: Q&A