## Slide 1: Project: Training(MAGENTO). Week: 50 Leader: NhanCT
Overall Status
Overview and Purpose
- Training & support to develop magento’s extension.
Assign Head Count: 3
Deadline: 2016/12/23
Estimation: 3 MM
Achievements Last Week
completed training phase
Next Week
Open new training phase and waiting development plan
Decisions Required
Blue
-.
Metrics
Measurement Method /Success Criteria
QA: 0/0; Issues: 3/5
Delay: None
Major Milestones
Risk and Issues
MD | Activity | Planned | Actual
100 | Training | 2016/12/07 | 2016/12/07
36 | Training 2 | 2016/12/23 | 
Issue | Root Cause | Proposed Solution /Action
Members have skill enough to develop but we have development plan with TCI |  | 
About deployment of Magento Portal, SI team need senior Magento Engineer to do the tasks but my team have no any senior. |  | Confirm to SI and define task list and get support from other team.

## Slide 2: Available resources in week 50
 | Name | Mon | Tue | Wed | Thu | Fri | Sat | Avg
1 | Chau Thanh Nhan | 100% | 100% | 100% | 75% | 75% |  | 90%
2 | Nguyen Cong Binh | 100% | 100% | 100% | 100% | 100% |  | 100%
4 | Vu Duc Thuan | 100% | 100% | 100% | 100% | 00% |  | 80%
5 | Bui Viet Huong | 100% | 100% | 100% | 100% | 100% |  | 100%
Notes: 高さ：11.5、幅：25、横位置：0.14 cm、縦位置：2.06 cm

## Slide 3: Tasks W50
 | Task | Phase | Start Date | Due Date | Status | Actual | Next Week
1 | [NO 9-267] Translation Extension | OJT | 11/10/2016 | 11/25/2016 | Completed | 100% | 100%
2 | [No 1-2] Member Information Registration-Email address identity confirmation | OJT | 11/21/2016 | 11/28/2016 | Completed | 94% | 100%
3 | [No 1-3]Member Information Registration-Confirmation for inputted member information | OJT | 11/21/2016 | 11/30/2016 | Completed | 100% | 100%
4 | [No 3-44]会員系サービス管理-サイト利用規約設定 | OJT | 11/21/2016 | 12/05/2016 | Completed | 78% | 100%
5 | [No 3-60]会員管理-会員情報の代理登録 | OJT | 11/18/2016 | 11/30/2016 | Completed | 84% | 100%
6 | [NO 9-267] Upgrade Translation Extension v2 | OJT2 | 12/01/2016 | 12/06/2016 | In Progress | 47% | 100%
7 | [1-36]Membership related services-Print the detais of an order | OJT2 | 12/13/2016 | 12/23/2016 | Open | 0% | 20%
8 | [1-25]Membership related services-Multiple steps for rank change | OJT2 | 12/7/2016 | 12/23/2016 | In Progress | 5% | 30%
9 | [1-28]Membership related services-Notification email of the rank update | OJT2 | 12/12/2016 | 12/23/2016 | Open | 0% | 20%
11 | Reaserch Magento validation | OJT2 | 12/7/2016 | 12/9/2016 | Completed | 100% | 100%
Notes: 高さ：11.5、幅：25、横位置：0.14 cm、縦位置：2.06 cm

## Slide 4: Issues W50
 | Issue | Cause | Action | Status
1 | Mr Duy will resign next week |  |  | Occurred
2 | Vaimo’s Development Environment is MacOS |  | Member will development on Windows Environment, PL will check source code on Mac Environment before release to customer | Not Yet
3 | Mr Dang moved to NihonTyokuhan team | Request by SPM | approved | Occurred
4 | Members have skill enough to develop but we have development plan with TCI |  |  | 
5 | About deployment of Magento Portal, SI team need senior Magento Engineer to do the tasks |  | Confirm to SI and define task list and get support from other team. | Occurred
Notes: 高さ：11.5、幅：25、横位置：0.14 cm、縦位置：2.06 cm

## Slide 5: Other