## Phase
| Statements | Rating | Rating | Rating | Rating
1 | The PM led and motivated the project team. | 3 | 3 | 2 | 3 | 11/12
2 | The PM was open to suggestion and comments. | 2 | 3 | 2 | 3 | 10/12
3 | The PM made ethical project decisions. | N/A | N/A | 2 | 3 | 5/12
4 | The project objectives were clear to me. | 3 | 3 | 3 | 2 | 11/12
5 | The project was well supported by management. | 3 | N/A | 1 | 2 | 6/12
6 | The project meeting were effective. | 2 | 2 | 2 | 3 | 9/12
7 | We worked well together cross-functionally. | N/A | 3 | 2 | 2 | 7/12
8 | Out project management processes were effective. | 2 | 3 | 3 | 3 | 11/12
9 | Our technical execution strategies were effective. | 3 | 2 | 3 | 3 | 11/12
Please input your comment which you want to share to team and learn from this project
Your comments
- Processes ( learn lession/ your improvement) - Business System ( learn lession/ your improvement) - Technology ( learn lession/ your improvement) - System Tool ( learn lession/ your improvement)

## BinhNC
Statements
1 | Well organized, and attends meeting on time. | o | o | o | +
2 | Make positive contributions to the overall project effort. | + | o | + | +
3 | Displays technical competence. | o | + | o | +
4 | Take appropriate responsibility. | + | o | o | +
5 | Works well under pressure. | o | o | + | +
6 | Works well with stakeholders. | + | + | o | +
7 | Communicates well with team members | + | + | o | +
8 | Produces high quality work. | o | o | + | +

## DangLH
Statements
1 | Well organized, and attends meeting on time. | o | o | o | +
2 | Make positive contributions to the overall project effort. | + | o | + | +
3 | Displays technical competence. | + | o | + | +
4 | Take appropriate responsibility. | + | o | o | +
5 | Works well under pressure. | + | o | + | +
6 | Works well with stakeholders. | + | + | o | +
7 | Communicates well with team members | + | + | o | +
8 | Produces high quality work. | o | o | + | +

## NhanCT
Statements
1 | Well organized, and attends meeting on time. | + | o | o | +
2 | Make positive contributions to the overall project effort. | o | + | + | +
3 | Displays technical competence. | + | + | o | +
4 | Take appropriate responsibility. | + | + | o | +
5 | Works well under pressure. | + | o | o | +
6 | Works well with stakeholders. | + | + | o | +
7 | Communicates well with team members | + | + | o | +
8 | Produces high quality work. | o | + | + | +

## ThuanVD
Statements
1 | Well organized, and attends meeting on time. | o | o | o | o
2 | Make positive contributions to the overall project effort. | o | o | o | o
3 | Displays technical competence. | o | o | o | o
4 | Take appropriate responsibility. | + | o | o | o
5 | Works well under pressure. | o | o | + | o
6 | Works well with stakeholders. | + | + | o | o
7 | Communicates well with team members | + | + | o | o
8 | Produces high quality work. | o | o | + | o