## Review Log
No. | Review Date | Reviewed | Function | Document Type | Defect Type | Defect | Action | Reviewer | Finished Date | Status | Notes / Comment
1 | 2016-10-12 | Binh | [No 3-44]会員系サービス管理 | Basic Design | Logic | Describe input/out data each file |  | Nhan | 2016-12-06 | Fixed
2 | 2016-11-29 | Binh | [No 3-44]会員系サービス管理 | Detail Design | Logic | Describe input/out data each file | Describe at registration.php. | Nhan | 2016-12-07 | Fixed
3 | 2016-11-19 | Binh | [No 3-44]会員系サービス管理 | Detail Design | Lack Information | Describe memo on xml/phtml file | Describe at register.phtml, customer_account_create.xml, module.xml. | Nhan | 2016-12-08 | Fixed
4 | 2016-11-30 | Huong | [No 1-3]Member Information Registration | Test Design | Lack Information | Don’t update Cover page |  | Nhan | 2016-12-09 | Fixed
5 | 2016-11-30 | Huong | [No 1-3]Member Information Registration | Test Design | Lack Information | MOCKUP DESIGN sheet incorrect |  | Nhan | 2016-12-10 | Fixed
6 | 2016-11-30 | Huong | [No 1-3]Member Information Registration | Test Design | Lack Information | Test Result incorrect (only describe updated screen) |  | Nhan | 2016-12-11 | Fixed
7 | 2016-12-01 | Huong | [No 1-3]Member Information Registration | Test Design | Logic | content of detail sheets did not match screen structure documents |  | Nhan | 2016-12-12 | Fixed
8 | 2016-12-02 | Thuan | [No 1-2] Member Information Registration | Test Design | Mis-understand | Content of Mockup Design does not be based on Basic Design | Delete all and do again | Nhan | 2016-12-13 | Fixed
9 | 2016-12-03 | Thuan | [No 1-2] Member Information Registration | Test Design | Mis-understand | Sheet: Test Result Summary Require Email Configuration is unescessary -> should update F010 sheet | Delete all and do again | Nhan | 2016-12-14 | Fixed
10 | 2016-12-04 | Thuan | [No 1-2] Member Information Registration | Test Design | Mis-understand | Sheet: Overall Result Data is incorrect | Delete all and do again | Nhan | 2016-12-15 | Fixed
11 | 2016-12-05 | Thuan | [No 1-2] Member Information Registration | Test Design | Mis-understand | Sheet: F010 Result Data is incorrect | Delete all and do again | Nhan | 2016-12-16 | Fixed
12 | 2016-12-05 | Binh | [No 3-44]会員系サービス管理 | Test Design | Lack Information | Cover page is incorrect | Delete Customer name | Nhan | 2016-12-17 | Fixed
13 | 2016-12-06 | Binh | [No 3-44]会員系サービス管理 | Test Design | Lack Information | Sheet Overrall Result: Creator is incorrect | Fix to "Binh" | Nhan | 2016-12-18 | Fixed
14 | 2016-12-07 | Binh | [No 3-44]会員系サービス管理 | Test Design | Mis-understand | Screen does not match as Screen Layout | Change image at Mockup design | Nhan | 2016-12-19 | Fixed
15 | 2016-12-08 | Binh | [No 3-44]会員系サービス管理 | Test Design | Lack Information | Make detail item each condition | Add input value for each condition | Nhan | 2016-12-20 | Fixed
16 | 2016-12-09 | Binh | [No 3-44]会員系サービス管理 | Test Design | Lack Information | Delete unnescessary sheets | Hide sheets not nescessary | Nhan | 2016-12-21 | Fixed
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Chart
Basic Design | 1
Detail Design | 2
Database Design | 0
Test Design | 13
Total | 16
Feedback | 0
Change Request | 0
New Request | 0
Mis-understand | 5
Lack Information | 6
Logic | 1
Total | 12

## Combo
Category | Status
Feedback | Create New
Change Request | Fixed
New Request | Closed
Mis-understand | Canceled
Lack Information
Logic
Functions
[NO 9-267] Translation Extension
[No 3-60]会員管理-会員情報の代理登録
[No 1-2] Member Information Registration
[No 1-3]Member Information Registration
[No 3-44]会員系サービス管理
Defect Type
Basic Design
Detail Design
Database Design
Test Design